NIED Statement of Work
September 17, 2012
Company Information:

Business Name :
Far East Controls LLC

Sole Proprietor:

Rodney L. Larson




P.O. Box 44847




Eden Prairie, MN 55344

Philippine Contact Information:




c/o Nelson Lumbre




Isagani




Maasin City




Southern Leyte




Philippines  6600

952-960-1935 Vonage Phone that Rings in Maasin

(local call from MN)

+63-906-277-4003
Cell Phone in Maasin

+63-53-570-9048
Land-Line in Maasin

The starting date for on-site work to commence at the NIED Shaking Table in Miki, Japan is tentatively set for December 10, 2012 through December 22, 2012.

Deliverables:
1. System support and tuning of the NIED Shaking Table required by the Table Controller software changes to disable some number of the system’s actuators to make it possible to run the table longer. This will make it possible for the NIED system to run the March 2012 Tsunami Earthquake. It is necessary to perform the following steps in co-operation with the NIED system’s operating staff and should take 2 weeks of effort. 

The first week’s efforts shall include the following objectives:
· Verify that the software changes are correctly controlling the Shaking Table.

· Verify that the software can be changed to use different choices of which actuators to disable.

· Verify that the software can be changed to use different choices of which actuators to disable.

2. After verification of the new controls, the following work shall be done:

· Tune the Shaking Table for the 3 main actuator configurations that have been specified by the NIED customer.

· Assist in running the March 2012 Earthquake on the empty Shaking Table.
· Train the NIED Operating Staff on how to alter the configurations and to tune the Shaking Table for this reduced maximum force performance.
NIED Statement of Work

September 17, 2012

Rates/Payment Terms:
	Payments
	Amount
	When

	Airfare + Hotel
	 (work with MTS Travel Representative)
	Billed after successful completion of deliverables

	Deliverable 1 (week 1)
	$4080 + per diem for 6-day work week
	Billed after successful completion of deliverables

	Deliverable 2 (week 2)
	$4080 + per diem for 6-day work week
	Billed after successful completion of deliverables


Presented by:  ___________________
Submitted by: ________________________           Rod Larson, FEC LLC


     David Kusner, PE
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